Appendix L

Turnkey EPC BESS Indicative Term Sheet

The following are terms that Syrcuit Energy Solutions, Inc. (the “Buyer” or “Owner”) expects to include in the eventual Turnkey Engineering, Procurement, and Construction (EPC) Battery Energy Storage System (BESS) Agreement (the “Agreement”) with [Contractor Name] (the “BESS Contractor”) for the [Project Name] BESS (the “Project”). It is intended that the terms and conditions of the Agreement will be based on the provisions contained in this Term Sheet; however, this Term Sheet does not address all terms and conditions that will be required for a definitive agreement.

| # | Provision | Description |
| --- | --- | --- |
|  | Owner | Syrcuit Energy Solutions |
|  | BESS Contractor | [Contractor Name] |
|  | Project Name | [Project Name] BESS |
|  | Project Location | [County Name], [State] |
|  | Lat/Long | [Latitude]/[Longitude] |
|  | Site Elevation | Approx. [XXX] meters above sea level |
|  | Target Commercial Operation Date (COD) | [Project Guaranteed COD Note: Bidders can view Project CODs in the RFP Instructions. |
|  | Guaranteed Substantial Completion Date | [Contractor Guaranteed Substantial Completion Date |
|  | Expected Delivery Date | [Contractor Provided Months] before COD |
|  | Guaranteed Delivery Date | [Contractor Guaranteed Delivery Date] |
|  | Delivery Point | [Contractor Defined Delivery Point (warehouse or site)] |
|  | Guaranteed Power - AC Usable Power at the Point of Interconnection (POI) | [Contractor Guaranteed Power] MW |
|  | Guaranteed Energy (usable at the POI net of Station Power usage) at Continuous Power (CP) | [Contractor Guaranteed Energy] MWh at Substantial Completion ([Contractor Guaranteed Power] MW over {Required Duration] hours) BESS Contractor to include annual Guaranteed Capacity values for years 0-20 of the LTSA term (see Annual Guaranteed Energy Capacity Table herein under Performance Guarantees & Liquidated Damages) |
|  | Capacity Retention | Maintain power and energy capacity for 20 years at the POI |
|  | BESS Duty Cycle | BESS Contractor to assume 365 full equivalent (100%) depth of discharge (DOD) cycles per year, up to 2 cycles per day |
|  | BESS Design Life | 20 Years |
|  | Guaranteed Round-Trip Efficiency (RTE) at the POI | [Contractor Guaranteed RTE] 86% minimum Beginning-of-life (BoL) at Substantial Completion. BESS Contractor to include annual round-trip efficiency degradation table for years 0-20 of the LTSA term (see Annual Guaranteed Round-Trip Efficiency Table herein under Performance Guarantees & Liquidated Damages) |
|  | POI | Revenue meter to be located on the primary side of the primary side of the Medium Voltage Transformer (MVT)]. |
|  | Revenue Meter | The Project’s Revenue Meter shall mean the utility/ISO-approved settlement meter, located at the POI. |
|  | Reactive Power | +[0.95/-0.95] at [Guaranteed Power] at POI Set point control +1…-1 as inverter capability allows. |
|  | Auxiliary Power / Station Power | Must be separately metered. BESS Contractor to provide station service sizing and associated storage sizing methodology and options for evaluation. |
|  | Scope of Work | The BESS Contactor shall engineer, supply, deliver, construct, install, integrate, and commission a turn-key BESS, including the minimum, the following scope of work: - Battery Systems: Contractor shall supply battery systems to include battery racks, containing battery modules, within an enclosure integrated with onboard thermal management, Battery Management System (BMS), Fire Protection System (FPS), internal protection, monitoring, and other systems as needed within the enclosure(s), certified with applicable codes and standards. - Bidirectional Power Conversion System (PCS): Contractor shall supply PCS (internal string, modular, or central). - Medium-Voltage Transformer (MVT): Contractor shall supply the MVT (can be PCS/MVT skid solution). - Additional Balance of Plant (BOP) Equipment: Contractor shall supply any additional BOP equipment, supplies, machinery, and tools required to deliver a fully operational site, to include at minimum: Medium-Voltage Switchgear (MVSG), LV auxiliary transformers, field network enclosures (FNEs), switchboards, DC conduit, and wiring between BESS Facility equipment to the POI. - EMS: Contractor shall provide an EMS and device integration with controllers, HMI, SCADA, networking, communications, and cybersecurity. - Commissioning: Contractor shall perform Original Equipment Manufacturer (OEM) cold and hot commissioning of the provided equipment, unit- and site-level commissioning, and Substantial Completion Testing. - Warranty and Performance Guarantees (PFG): The Contractor shall supply pricing and details for a standard warranty and Performance Guarantees covering the equipment and services provided. - Shipping: Contractor shall provide pricing to include Delivered Duty Paid (DDP). - Long-term Service Agreement (LTSA): The Contractor shall supply an LTSA template with annual pricing for preventative maintenance and corrective maintenance, warranty, and performance guarantees. - EPC: Contractor shall provide engineering design, equipment procurement, construction, and commissioning services required to deliver a fully operational BESS to the POI, including but not limited to permitting, receiving/handling/transport, installation, site safety, and coordination. |
|  | Contract Price | Owner shall pay to BESS Contractor the agreed upon amount (USD $[___]) specified in the Agreement (the “Contract Price”), which shall be determined in accordance with the pricing mechanisms set forth in the Agreement. The Contract Price shall be inclusive of all taxes, other fees, assessments or charges payable by BESS Contractor in conjunction with delivering and installing the BESS Equipment at the project site, including all import duties and export duties from the jurisdiction from which the BESS Equipment may be shipped. The Parties agree that the Contract Price excludes materials, supplies, equipment and other items that are tax exempt under applicable laws. Each Party shall be responsible for its own income taxes. |
|  | Milestone Payment Schedule | Milestone; Milestone ID; Milestone Completion Date; Payment; Payment Amount ($). Effective Date of the Agreement; A; [Contractor Input]; [10]% of Imputed Contract Price*; [BESS Contractor Input]. BESS Contractor’s release of equipment for manufacturing; B; [Contractor Input]; [15]% of Contract Price; [BESS Contractor Input]. Upon completion of FAT at BESS Contractor’s factory; C; [Contractor Input]; [25]% of Contract Price; [BESS Contractor Input]. Equipment delivery to Delivery Point; D; [Contractor Input]; [30]% of Contract Price; [BESS Contractor Input]. Substantial Completion; E; [Contractor Input]; [20]% of Contract Price; [BESS Contractor Input]. |
|  | Eligible Change in Tariff | “Eligible Change in Tariff” means (i) any duty, tariff, import tax, or other similar import fee or cost that becomes effective after, or the enforcement of which commences after, the Agreement’s Effective Date, or (ii) any increase to the applicable rate of any of the foregoing which becomes effective after the Effective Date, to the extent affecting the Project; in either case, provided that it was not foreseeable by a reasonably prudent person as of the Effective Date and not caused by BESS Contractor’s violation or non-compliance with any applicable law or breach of the Agreement. To the extent an Eligible Change in Tariff occurs after the Effective Date that would increase BESS Contractor’s costs, BESS Contractor may be entitled to a Change Order to increase the Contract Price as follows: - BESS Contractor shall be responsible for the portion of an Eligible Change in Tariff resulting in an increase of up to ten percent (10%) of the Contract Price. - For an Eligible Change in Tariff that results in a tariff increase above ten percent (10%) and up to twenty percent (20%) of the Contract Price, BESS Contractor shall be entitled to a Change Order to increase the Contract Price for fifty percent (50%) of the tariff increase in this range. - Owner shall be responsible for the portion of an Eligible Change in Tariff resulting in an increase above twenty percent (20%) of the Contract Price; provided, however, that Owner shall have the right to terminate the Agreement. If any anticipated tariffs that have been assumed in the Contract Price are reduced, Owner shall have the right to a Change Order to obtain a dollar-for-dollar decrease in the applicable Contract Price by the amount of such reduction. |
|  | Invoicing / Payments | Payment terms are net 60 days from the Owner’s receipt of the BESS Contractor’s correctly rendered invoice, unless otherwise stated in the Agreement. |
|  | Delivery Delay LDs | Delivery Delay Liquidated Damages (“Delivery Delay LDs”) of (a) $100/MW per day multiplied by the Project’s Guaranteed Power capacity for each day equipment delivery is delayed beyond the Guaranteed Delivery Date up to and including fifteen (15) days after the Guaranteed Delivery Date, (b) plus $200/MW per day multiplied by the Project’s Guaranteed Power capacity for each day after the fifteenth (15th) day following the Guaranteed Delivery Date, up to and including the sixtieth (60th) day following the Guaranteed Delivery Date, and (c) plus $500/MW per day multiplied by the Project’s Guaranteed Power capacity for each day delayed thereafter. |
|  | Substantial Completion Delay LDs | Substantial Completion Delay Liquidated Damages (“SC Delay LDs”) of (a) $200/MW per day multiplied by the Project’s Guaranteed Power capacity for each day Substantial Completion is delayed beyond the Guaranteed COD up to and including fifteen (15) days after the Guaranteed COD, (b) plus $350/MW per day multiplied by the Project’s Guaranteed Power capacity for each day after the fifteenth (15th) day following Guaranteed COD, up to and including the sixtieth (60th) day following the Guaranteed COD, and (c) plus $500/MW per day multiplied by the Project’s Guaranteed Power capacity for each day delayed thereafter. |
|  | Delay Liquidated Damages Cap | The aggregate cap of the Delivery Delay LDs and SC Delay LDs shall be 20% of the Contract Price. |
|  | Performance Guarantees & Liquidated Damages | The “Performance Guarantees” refer to the following minimum performance standards that the BESS must achieve during Substantial Completion testing as well as during the twenty (20) year LTSA term. Guaranteed Power Annual power capacity performance tests will be performed. - Performance Level: Guaranteed Power at the POI - Liquidated Damages (LDs): (Guaranteed Power - Measured Power) x $150/MW-day - Event of Default: if the average measured power capacity is below the Guaranteed Power Capacity for a period of twelve (12) consecutive months Guaranteed Energy Annual capacity performance tests will be performed. - Performance Level: Guaranteed Energy at the POI per the table below and no deductible concepts will be accepted; - LDs: (Guaranteed Energy - Measured Energy) x $150/MWh-day - Event of Default: if Measured Energy is below Guaranteed Energy for a period of 12 consecutive months Annual Guaranteed Energy Capacity Table Year after COD; Guaranteed Energy (MWh). 0; [Contractor to Input MWh]. 1; [Contractor to Input MWh]. 2; [Contractor to Input MWh]. 3; [Contractor to Input MWh]. 4; [Contractor to Input MWh]. 5; [Contractor to Input MWh]. 6; [Contractor to Input MWh]. 7; [Contractor to Input MWh]. 8; [Contractor to Input MWh]. 9; [Contractor to Input MWh]. 10; [Contractor to Input MWh]. 11; [Contractor to Input MWh]. 12; [Contractor to Input MWh]. 13; [Contractor to Input MWh]. 14; [Contractor to Input MWh]. 15; [Contractor to Input MWh]. 16; [Contractor to Input MWh]. 17; [Contractor to Input MWh]. 18; [Contractor to Input MWh]. 19; [Contractor to Input MWh]. 20; [Contractor to Input MWh]. Guaranteed RTE RTE is the measured rate of efficiency comparing a unit of energy injected into the BESS and the amount of that unit of energy discharged by the energy storage system at the POI: - Performance Level: BESS Contractor to provide a Guaranteed RTE using the following table and no deductible concepts will be accepted; - LDs: (Guaranteed RTE – Measured RTE) x cumulative charged energy during shortfall period x $150/MWh Event of Default: Measured RTE falls below 80.0% Annual Guaranteed Round-Trip Efficiency Table Year after COD; Guaranteed Round-Trip Efficiency (%). 0; [Contractor to Input %]. 1; [Contractor to Input %]. 2; [Contractor to Input %]. 3; [Contractor to Input %]. 4; [Contractor to Input %]. 5; [Contractor to Input %]. 6; [Contractor to Input %]. 7; [Contractor to Input %]. 8; [Contractor to Input %]. 9; [Contractor to Input %]. 10; [Contractor to Input %]. 11; [Contractor to Input %]. 12; [Contractor to Input %]. 13; [Contractor to Input %]. 14; [Contractor to Input %]. 15; [Contractor to Input %]. 16; [Contractor to Input %]. 17; [Contractor to Input %]. 18; [Contractor to Input %]. 19; [Contractor to Input %]. 20; [Contractor to Input %]. Guaranteed Availability Availability is defined as the number of hours in the period the Project is online and capable of providing the Guaranteed Energy and Guaranteed Power in any calendar year, divided by the total number of hours in the calendar year, excluding planned maintenance outages and other excused events. - Performance Level: 97% Guaranteed Availability (annual availability guarantee commencing at COD) - LDs: (Guaranteed Availability – Measured Availability) x Days in month x $150/MWh/day - Event of Default: if the average Measured Availability for any rolling 12-month period falls below 80% |
|  | Performance Buydowns | Performance LDs are the sole and exclusive remedy for performance shortfall. There are no “buydown” liquidated damages payable which allow BESS Contractor to (i) declare Substantial Completion with less than one hundred percent (100%) of contracted capacity, or (ii) deliver something less than the Project’s full Performance Guarantees. |
|  | Performance Guarantee Liquidated Damages Cap | The aggregate cap of the aforementioned Performance Guarantee related liquidated damages (Guaranteed Power, Guaranteed Energy, Guaranteed RTE, Guaranteed Availability) during the LTSA term shall be equal to 20% of the Agreement’s Contract Price. Performance liquidated damages are the sole and exclusive remedy for performance shortfalls. |
|  | Testing | BESS Contractor to perform and provide the following test results: - Factory Acceptance Test (FAT) test results for all major equipment supplied; and - Cold and hot commissioning for all major equipment supplied; The BESS Contractor will provide technical support for: - Hot Commissioning Verification Test and Substantial Completion Testing. |
|  | Agreement Termination / Events of Default | Pre-Substantial Completion Termination: Prior to the Project achieving Substantial Completion, the Project is subject to termination by Owner if the Project fails to achieve Substantial Completion, by fault of the BESS Contractor, by whichever occurs first: sixty (60) days after the Guaranteed Substantial Completion Date, or the Delay Liquidated Damages Cap is reached. In the event of a pre-SC termination as defined above, or in connection with an Event of Default that occurs pre-SC, BESS Contractor shall pay a termination payment. BESS Contractor Event of Default Termination: BESS Contractor shall be in default of its obligations pursuant to this Agreement upon the occurrence of any one or more events of default: - bankruptcy of a party; - failure to maintain insurance of the required types and amounts; - failure to achieve a critical milestone(s); - failure to meet Performance Guarantees; and - reaches the Delay Liquidated Damages Cap. Termination for Convenience: Owner may terminate the Agreement, for convenience, at any time, upon 10 days’ written notice to BESS Contractor, and Owner shall pay a termination payment. |
|  | Confidentiality | The Agreement will provide for customary confidentiality obligations of the Parties. |
|  | Operations and Maintenance (O&M) | If an LTSA is executed with BESS Contractor: - Owner shall, at all times, retain unrestricted operational control of the Project and be responsible for dispatching and coordinating the charging of the Project. - BESS Contractor shall, at all times, retain all other aspects of operation and maintenance of the Project in accordance with good utility practice and applicable law and adhering to all operational data, interconnection and telemetry requirements applicable to the Project. - BESS Contractor’s O&M obligations shall include the obligation to repair and/or replace batteries and other equipment, or to install additional batteries and equipment as needed to maintain compliance with the Performance Guarantees. - Owner shall provide electric service required to operate and maintain the Project, used to maintain and operate the Project. - LTSA shall contain other provisions normal and customary for operation and services agreements, including but not limited to, representations and warranties, ownership of data, confidentiality, software updates, hazardous materials, terminations and transition services, etc. |
|  | Serial Defect | If a defect exists with respect to 10% of any major component in the Project, BESS Contractor shall perform a root cause analysis of such defect and perform full replacement of that corresponding component within the Project. |
|  | Prevailing Wage, & Domestic Content (If Applicable) & FEOC | PWA: Prevailing Wage and Apprenticeship (PWA) Requirements, shall apply to any (i) directly or indirectly funded project or programs pursuant to the Jobs Act (ii) federal infrastructure project pursuant to Buy America and Buy American (iii) and pursuant to State law and pursuant to Sections 48(a)(10) and (11), 45(b)(7) and (8), 48E(d)(3) and (4) and 45Y(g)(9) and (10) of the Internal Revenue Code (IRC), and the regulations and guidance issued thereunder. Domestic Content (Optional): The Project will qualify for the domestic content bonus credit under Section 48E(a)(3)(B) of the IRC under the updated elective safe harbor for the domestic content bonus credit described in IRS Notice 2025-8 (or subsequently issued applicable notice or regulations, and BESS Supplier shall provide back-up information and certifications required to support such treatment (including at least 50% domestic content) and satisfy any required reporting requirements, such back-up and support to be reasonably satisfactory to Owner. FEOC: Supplier will represent and warrant that on and as of (i) the Effective Date, and (ii) (A) January 1, 2026, (B) each December 31 during the period that ends one year after the date that Owner’s final payment is made to Buyer for the System under this Agreement during the 10 year period from and after the Project’s commissioning date (each of the Effective Date, January 1, 2026, and each such December 31, a “Representation Date”), and (C) the date of each invoice for payment under this Agreement, the delivery of which to Owner shall be deemed to include making such representations and warranties that Supplier is not a Prohibited Foreign Entity with the meaning of Section 7701(a)(51) and any guidance or regulations issued thereunder. Notwithstanding anything to the contrary in this Agreement, the Parties intend and agree that none of the transactions contemplated by this Agreement are intended or expected to grant Supplier (or any other Party) “effective control” of Owner or the Project within the meaning of Section 7701(a)(51)(D)(i)(II)(aa) and Section 7701(a)(51)(D)(ii) of the IRC, including any unrestricted contractual right to determine the amount or timing of activities related to the production or storage of electricity in the Project. |
|  | Assignment | The Agreement may not be assigned by any party without the prior written consent of the other party. |
|  | Confidentiality | The Agreement will provide for customary confidentiality obligations of the Parties. |
|  | Governing Law | This Term Sheet and the definitive documents will be governed by the laws of the State of [Project State] and the parties submit to the exclusive jurisdiction of state and federal courts in [Project State]. |

Each of the parties acknowledges their acceptance of the terms and conditions relating to the proposed transaction described herein by executing the acknowledgement below:

| [OWNER] |  | [BESS CONTRACTOR] |  |  |  |
| --- | --- | --- | --- | --- | --- |
| By: | ____________________ | By: | ____________________ |  |
| Name: | ____________________ | Name: | ____________________ |  |
| Title: | ____________________ | Title: | ____________________ |  |
| Date: | ____________________ | Date: | ____________________ |  |

Contractor to review Appendix H1 and H2 – Substantial Completion Test Plans.